## Product Backlog
Health Care Website using ML
8 months Deployment Timeline
Month 1–2: Project Planning & Foundation | Priority | Planned Days | Used Days | Work Progess
Requirement gathering : Analyze business needs, personas, and competitors, focusing on scheduling, symptom checker, and patient dashboard. | High | 15 Days | 12 Days | Completed
Tech Stack Selection: Select front-end (React), back-end (Node.js), database (MongoDB), cloud (AWS), and ML tools (TensorFlow). | Medium | 5 Days | 5 Days | Completed
UI/UX Design: Create wireframes, prototypes, and visual designs for key pages, focusing on intuitive interfaces for healthcare users. | Medium | 20 Days | 19 Days | Completed
Month 3–4: Back-End and Front-End Foundation
Back-End Development (Phase 1): Set up database for user data, appointments, ML outputs; implement secureauthentication. | High | 20 Days | 22 Days | Completed
Front-End Development (Phase 1): Develop responsive login, registration, and landing pages based on designs. | High | 20 Days | 18 Days | Completed
Month 5–6: Machine Learning and Feature Development
ML Model Development: Preprocess healthcare data to train ML models. | Medium | 20 Days | 20 Days | Completed
Feature Integration: Integrate ML models with front-end and back-end | High | 20 Days | 20 Days | Completed
Month 7–8: Testing, Compliance, and Deployment
Quality Assurance & Compliance: Test functionality ,performance, and security; validate ML predictions and ensure regulatory compliance (e.g., HIPAA, GDPR). | High | 23 Days | 23 Days | Completed
Deployment & Launch: Deploy on cloud with CI/CD; monitor feedback and resolve critical issues. | High | 21 Days | 21 Days | Completed

## Sprint Mangement
Sprint Management
Month | Sprint | Sprint Duration | Sprint Desc | Team Included | Sprint Wise Budget
Month 1 | Sprint 1 | 2 Weeks | Planning and UI/UX Design | Project Manager, UI/UX Designer, Compliance Specialist. | 210000
| Sprint 2 | 2 Weeks | Back-End Architecture Design | Back-End Developer, Compliance Specialist. | 180000
Month 2 | Sprint 3 | 2 Weeks | Data Collection and Preprocessing | Data Scientist, ML Engineer | 270000
| Sprint 4 | 2 Weeks | Front-End Development (Phase 1) | Front-End Developer, UI/UX Designer. | 190000
Month 3 | Sprint 5 | 2 Weeks | ML Model Training and Evaluation | ML Engineer, Data Scientist. | 270000
| Sprint 6 | 2 Weeks | Integration of Front-End, Back-End, and ML Models | Front-End Developer, Back-End Developer, ML Engineer | 270000
Month 4 | Sprint 7 | 2 Weeks | QA Testing and Compliance Validation | Tester, Compliance Specialist. | 180000
| Sprint 8 | 2 Weeks | Deployment and Launch | DevOps Engineer, Entire Team. | 1000000

## Sprint 1
| DO | Sprint | Time Period | Work Assignee |  | TASK | Priority | Work Progess
Month 1 | Planning and UI/UX Design | Sprint 1 | 2 WEEKS | Project Manager, UI/UX Designer, Compliance Specialist. |  | We define requirements, create wireframes and prototypes, and deliver the project plan with approved designs. | Medium | Completed
Budget
| Total Budget | Received Amount | Balance Payment |  | Saved Amount
| 2570000 | 210000 | 2360000 |  | 3000
Expenses
| Work Assignee | Cost | Setup Costs
| Project Manager | 45000 | 57500
| UI/UX Designer | 56000
| Compliance Specialist | 49000
| Total | 150000 | 57500
| Total Amount Spend | 207500

## Sprint 2
| DO |  | Sprint | Time Period | Work Assignee |  | TASK | Priority | Work Progess
Month 1 | Back-End Architecture Design |  | Sprint 2 | 2 WEEKS | Back-End Developer, Compliance Specialist. |  | We design the database, set up authentication and data storage, and deliver the schema and back-end structure. | High | Completed
Budget
|  | Total Budget | Received Amount | Balance Payment |  | Saved Amount
|  | 2570000 | 180000 | 2180000 |  | 12000
Expenses
|  | Work Assignee |  | Setup Costs |  | Setup Costs
|  | Compliance Specialist |  | 50000 |  | 48000
|  | Back-End Developer |  | 70000
|  | Total |  | 120000 |  | 48000
|  | Total Amount Spend |  | 168000

## Sprint 3
| DO | Sprint | Time Period | Work Assignee |  | TASK | Priority | Work Progess
Month 2 | Data Collection and Preprocessing | Sprint 3 | 2 WEEKS | Data Scientist, ML Engineer |  | Collect and preprocess healthcare data, ensuring quality and readiness for training, with a clean, prepared dataset as the deliverable. | High | Completed
Budget
| Total Budget | Received Amount | Balance Payment |  | Saved Amount
| 2570000 | 270000 | 1910000 |  | 15000
Expenses
| Work Assignee | Cost | Development Costs
| Data Scientist | 72000 | 108000
| ML Engineer | 75000
| Total | 147000 | 108000
| Total Amount Spend | 255000

## Sprint 4
| DO |  | Sprint | Time Period | Work Assignee |  | TASK | Priority | Work Progess
Month 2 | Front-End Development (Phase 1) |  | Sprint 4 | 2 WEEKS | Front-End Developer, UI/UX Designer. |  | Build the front-end for the landing page, login, and registration with a responsive, user-friendly design. Deliverable: Static pages for the initial front-end. | High | Completed
Budget
|  | Total Budget | Received Amount | Balance Payment |  | Saved Amount
|  | 2570000 | 190000 | 1720000 |  | 12000
Expenses
|  | Work Assignee |  | Cost | Development Costs
|  | Front-End Developer |  | 52000 | 70000
|  | UI/UX Designer |  | 56000
|  | Total |  | 108000 | 70000
|  | Total Amount Spend |  | 178000

## Sprint 5
| DO | Sprint | Time Period | Work Assignee |  | TASK |  | Priority | Work Progess
Month 3 | ML Model Training and Evaluation | Sprint 5 | 2 WEEKS | ML Engineer, Data Scientist. |  | Train and evaluate machine learning models (e.g., symptom checker), optimizing for accuracy. Deliverable: Trained and evaluated models. |  | High | Completed
Budget
|  |  | Total Budget | Received Amount | Balance Payment |  | Saved Amount
|  |  | 2570000 | 270000 | 1450000 |  | 15000
Expenses
|  |  | Work Assignee | Cost | Model Development and Integration Costs
|  |  | ML Engineer | 75000 | 108000
|  |  | Data Scientist | 72000
|  |  | Total | 147000 | 108000
|  |  | Total Amount Spend | 255000

## Sprint 6
| DO | Sprint | Time Period | Work Assignee | TASK | Priority | Work Progess
Month 4 | Integration of Front-End, Back-End, and ML Models | Sprint 6 | 2 WEEKS | Front-End Developer, Back-End Developer, ML Engineer | Integrate the front-end, back-end, and ML models, testing real-time features. Deliverable: Fully functional system. | Medium | Completed
Budget
|  | Total Budget | Received Amount | Balance Payment | Saved Amount
|  | 2570000 | 270000 | 1180000 | 5000
Expenses
|  | Work Assignee | Cost | Integration Costs
|  | Front-End Developer | 52000 | 128000
|  | Back-End Developer | 85000
|  | Total | 137000 | 128000
|  | Total Amount Spend | 265000

## Sprint 7
| DO | Sprint | Time Period | Work Assignee | TASK | Priority | Work Progess
Month 4 | QA Testing and Compliance Validation | Sprint 7 | 2 WEEKS | Tester, Compliance Specialist. | Test the website for usability, performance, healthcare compliance, fixing bugs and validating ML predictions. Deliverable: Bug-free, compliant website. | Medium | Completed
Budget
|  | Total Budget | Received Amount | Balance Payment | Saved Amount
|  | 2570000 | 180000 | 1000000 | 6000
Expenses
|  | Work Assignee | Cost | Testing Costs
|  | Compliance Specialist | 49000 | 70000
|  | Tester | 55000
|  | Total | 104000 | 70000
|  | Total Amount Spend | 174000

## Sprint 8
| DO | Sprint | Time Period | Work Assignee | TASK | Priority | Work Progess
Month 4 | Deployment and Launch | Sprint 8 | 2 WEEKS | DevOps Engineer, Entire Team. | Deploy the website on a cloud platform with CI/CD, monitor user feedback, and address critical issues. Deliverable: Live healthcare website. | High | Completed
Budget
|  | Total Budget | Received Amount | Balance Payment | Saved Amount
|  | 2570000 | 1000000 | 0 | 40000
[6 empty] | Months | Total Sprintwise Profit
|  |  |  | Expenses |  | Sprint1 | 3000
[6 empty] | Sprint2 | 12000
|  | Work Assignee | Cost | Deployment and Launch Costs |  | Sprint3 | 15000
|  | Project Manager | 72000 | 170000 |  | Sprint4 | 12000
|  | UI/UX Designer | 56000 |  |  | Sprint5 | 15000
|  | Compliance Specialist | 49000 |  |  | Sprint6 | 5000
|  | Back-End Developer | 70000 |  |  | Sprint7 | 6000
|  | Data Scientist | 72000 |  |  | Sprint8 | 40000
|  | ML Engineer | 75000 |  |  |  | 108000 | Profit
|  | Front-End Developer | 52000
|  | Tester | 55000
|  | DevOps Engineer | 89000
|  | Total | 590000 | 170000
|  | Total Amount Spend | 760000

## monthly Payment
Salary of each Team Member
Work Assignee | Monthly | Total Salary
Project Manager | 72000 | 864000
UI/UX Designer | 56000 | 672000
Compliance Specialist | 50000 | 588000
Back-End Developer | 70000 | 840000
Data Scientist | 72000 | 864000
ML Engineer | 75000 | 900000
Front-End Developer | 52000 | 624000
Tester | 55000 | 660000
DevOps Engineer | 89000 | 1068000